## excel (1)
/Project/Clase SC_Lectura
PSP2.1 Project Plan Summary
Overall Metrics
Summary | Plan | Actual | To Date
Size/Hour | 7.15 | 8.76 | 25.2
Planned Time | 0.33333 |  | 0.5
Actual Time |  | 0.22361 | 0.36528
CPI (Cost-Performance Index) |  |  | 1.37
% Reuse | 0% | 0% | 0%
% New Reusable | 0% | 0% | 0%
Test Defects/KLOC or equivalent | 11.5 | 42.6 | 9.05
Total Defects/KLOC or equivalent | 28.7 | 63.8 | 22.6
Yield % | 60% | 33.3% | 60%
Code Review Rate | 58.4 | 35.2 | 126
% Appraisal COQ | 21.1% | 34.2% | 29.1%
% Failure COQ | 13.7% | 11.5% | 12.4%
COQ A/F Ratio | 1.54 | 2.97 | 2.35
PQI | 0.27 | 0.05 | 0.32
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Report generated at 9:01 PM on Dec 3, 2018